## Sheet1
Task | Status | Owner | Stage | Due date | Notes
Dataset Searching | Completed | Yomna, Naira, Omar | Post-event |  | skin, Brain, chest
Data1 preprocessing | Completed | marwan mohamedsaid | Post-event | 2026-03-04 | Model 1, Data 1
Data2 preprocessing | Completed | OMAR ELRayes | Post-event | 2026-03-04 | Model 1
Segmentation Model | Completed | Yomna Elhadad | Post-event | 2026-03-05 | Model 1 (Architecture & Training)
Augmentation & Data Merging | Completed | Naira Ahmed | Post-event | 2026-03-01 | Model 1
Cross Validation | Completed | Shaza | Post-event | 2026-03-05 | Model 1 (dice coef, kfold)
MLflow | Completed | marwan & omar | Pre-event |  | Model 1
Fast Api & back end | Completed | marwan & omar | Pre-event |  | connecting the 2 models
Seg-Model FineTuning | Completed | Yomna Elhadad | Post-event | 2026-04-04 | Model 1 (U-Net Vs Seg-Net Arch.)
Model 1 SteamLit | Completed | Naira |  | 4/14/2026 - 4/6/2026 | Model 1
Classification Model | Completed | Shaza | Post-event | 2026-04-06 | Model 2 (Building & Training & Visual)
API and Backend |  | omar & marwan |  |  | combining the 2 models
Planning the next phase |  | All |  | 17/4 - 26/4 | ideas, Data Gather,
Data Generation | Completed | Omar & Shaza | Post-event | 2026-04-27 | features & users
Database Designing | Completed | marwan | Pre-event | 2026-05-01 | ERD - Tables
usersData optimizing | Completed | Omar & Shaza | Post-event | 2026-05-14 | images links from main dataset
So_Far_Meeting | Completed | ALL |  | 2026-06-05 | What we have done so far and what's next
api deployement | Completed | Omar |  | 2026-06-05
Medical Chatbot | Completed | Naira & Omar & Yomna | Post-event | 2026-06-17 | genai , medical Qs
notebooks to modules | Completed | Yomna - Omar | Pre-event | 2026-07-05 | ready for production system
FrontEnd | Completed | Omar |  |  | Figma - lovable - stitchai